## Report
Property: |  | 210 W 31st Street
Project: |  | Demo/Redevelopment Project
Location: |  | NY, NY
Borrower: |  | Onyx 31st Street, LLC
Ownership Entity
Draw #: |  | 3
Period End Date: |  | 2015-12-30
Account Codes & Descriptions |  |  |  | BUDGET |  |  | COMMITMENTS, CHANGES & ESTIMATED FINAL COST | [5 empty] | PAYMENTS
[6 empty] | -1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12
[6 empty] | (2+1) | (1 or Actual Contracts) | (Detailed tracking required ) | (See Detail ) | (2+3+4) | (5-1) | (5/1) | (From Prior Report) | (See Detail ) | (8+9) | (10/5, must not be >100%) | (7-12, must not be a - value)
ID # | GL Code # | Job Code # | Description | Approved Budget | Reallocations & Approved Changes to Budget | TOTAL PROJECT BUDGET | Current Estimate or Committed Contracts | Approved Change Orders | Other Additions/ Modifications | Estimated Final Project Cost | Est. Variance vs. Current Approved Budget | Est. Cost vs Approved Budget | Costs Incurred Prior Period | Costs Incurred This Period | Total Costs to Date | % Complete | Balance to finish
1 |  |  | Counsel- Cole, Schotz |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 191979.11 | 26119.7 | 218098.81 | 0% | -218098.81
2 |  |  | Counsel- Greenberg Traurig |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 188829.19 | 0 | 188829.19 | 0% | -188829.19
3 |  |  | Professional Fees- ArchiData, Gensler, S&L Arch, Montrose, TPG |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 111385.46 | 0 | 111385.46 | 0% | -111385.46
4 |  |  | Acquisition Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 136346.24 | 6949 | 143295.24 | 0% | -143295.24
5 |  |  | St Mary- Capuchin - Option Payments |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 3677663.68 | 0 | 3677663.68 | 0% | -3677663.68
6 |  |  | Kevin Ward |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1000000 | 0 | 1000000 | 0% | -1000000
|  |  | Acquisition Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 5306203.68 | 33068.7 | 5339272.38 | 0% | -5339272.38
7 |  |  | Environmental Survey- NY Environmental | 4202 |  | 4202 | 4202 | 0 | 0 | 4202 | 0 | 100% | 3502 | 0 | 3502 | 83.34% | 700
8 |  |  | Environmental- Asbestos Abatement- Incinia / WCD | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 4868 | 4868 | 0% | -4868
9 |  |  | Architectural Services- SBLM | 8500 |  | 8500 | 8500 | 0 | 0 | 8500 | 0 | 100% | 8500 | 0 | 8500 | 100% | 0
10 |  |  | Construction- Installation- Vericon Construction | 137892 | 8644.62 | 146536.62 | 146536.62 | 0 | 0 | 146536.62 | 0 | 100% | 91081.05 | 55455.57 | 146536.62 | 100% | 0
11 |  |  | Permit Fees | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 375 | 0 | 375 | 0% | -375
12 |  |  | Utility Survey- Montrose Surveying Co, LLP | 3800 |  | 3800 | 3800 | 0 | 0 | 3800 | 0 | 100% | 3800 | 0 | 3800 | 100% | 0
|  |  | Side Yard Church Platform | 154394 | 8644.62 | 163038.62 | 163038.62 | 0 | 0 | 163038.62 | 0 | 100% | 107258.05 | 60323.57 | 167581.62 | 102.8% | -4543
13 |  |  | Architectural Services- SBLM | 7500 |  | 7500 | 0 | 0 | 0 | 0 | -7500 | 0% | 12816.89 | 0 | 12816.89 | 0% | -12816.89
14 |  |  | Furnish of Marketing Drape- TBD | 35188 |  | 35188 | 0 | 0 | 0 | 0 | -35188 | 0% | 15188.06 | 0 | 15188.06 | 0% | -15188.06
15 |  |  | Signage Consultant- Sensory Interactive / SBLM | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 10000 | 7100 | 17100 | 0% | -17100
34 |  |  | Installation of Banner- TBD | 70000 |  | 70000 | 0 | 0 | 0 | 0 | -70000 | 0% | 0 | 0 | 0 | 0% | 0
|  |  | Draping of Façade | 112688 | 0 | 112688 | 0 | 0 | 0 | 0 | -112688 | 0% | 38004.95 | 7100 | 45104.95 | 0% | -28004.95
16 |  |  | Clean-up/Minor Demo- Vericon | 121363 | 11363 | 132726 | 132726 | 0 | 0 | 132726 | 0 | 100% | 133031.42 | 0 | 133031.42 | 100.2% | -305.42
17 |  |  | 30th Street Church Lot Access Fee | 10000 |  | 10000 | 10000 | 0 | 0 | 10000 | 0 | 100% | 0 | 0 | 0 | 0% | 10000
18 |  |  | De-Branding / Secure Building- Vericon Construction | 20000 |  | 20000 | 20000 | 0 | 0 | 20000 | 0 | 100% | 23249.54 | 0 | 23249.54 | 116.2% | -3249.54
|  |  | Interior Clean Up/Minor Demo | 151363 | 11363 | 162726 | 162726 | 0 | 0 | 162726 | 0 | 100% | 156280.96 | 0 | 156280.96 | 96.04% | 9694.58
19 |  |  | Environmental Survey- WCD | 5200 |  | 5200 | 5200 | 0 | 0 | 5200 | 0 | 100% | 5050 | 0 | 5050 | 97.12% | 150
20 |  |  | Environmental Abatement- WCD (sub- Incinia) | 153473 |  | 153473 | 153473 | 0 | 0 | 153473 | 0 | 100% | 0 | 0 | 0 | 0% | 153473
21 |  |  | Site Surveys- Montrose | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 1000 | 1000 | 0% | -1000
22 |  |  | Architecture- Schematic Phase- SBLM | 30000 |  | 30000 | 30000 | 0 | 0 | 30000 | 0 | 100% | 22653.1 | 0 | 22653.1 | 75.51% | 7346.9
23 |  |  | Architecture- Design Development Phase- SBLM | 60000 |  | 60000 | 60000 | 0 | 0 | 60000 | 0 | 100% | 0 | 0 | 0 | 0% | 60000
24 |  |  | Geotech- Task 100- Surveys& TP's- Mueser Rutledge | 16000 |  | 16000 | 16000 | 0 | 0 | 16000 | 0 | 100% | 21332.1 | 0 | 21332.1 | 133.3% | -5332.1
25 |  |  | Geotech- Task 200- Boring Program- Mueser Rutledge | 20000 |  | 20000 | 20000 | 0 | 0 | 20000 | 0 | 100% | 26017.42 | 0 | 26017.42 | 130.1% | -6017.42
26 |  |  | Indoor/Outdoor Test Pits- JCoffey, Vericon | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 21868.14 | 0 | 21868.14 | 0% | -21868.14
27 |  |  | Indoor/Outdoor Boring- Aquifer Drilling & Testing | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 27096 | 0 | 27096 | 0% | -27096
28 |  |  | GC- General Conditions/ Consulting- Vericon Construction | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 6829.22 | 0 | 6829.22 | 0% | -6829.22
29 |  |  | Consultant Services- Budgeting Phase- Joe Denn | 25000 |  | 25000 | 25000 | 0 | 0 | 25000 | 0 | 100% | 0 | 0 | 0 | 0% | 25000
30 |  |  | Consultant Services- Schematic Phase Estimating- Vericon | 16000 |  | 16000 | 16000 | 0 | 0 | 16000 | 0 | 100% | 0 | 0 | 0 | 0% | 16000
31 |  |  | Consultant Services- DD Phase Estimating- Vericon | 13000 |  | 13000 | 13000 | 0 | 0 | 13000 | 0 | 100% | 0 | 0 | 0 | 0% | 13000
32 |  |  | Professional Fees- Schematic Phase Estimating- SBLM | 10000 |  | 10000 | 10000 | 0 | 0 | 10000 | 0 | 100% | 0 | 0 | 0 | 0% | 10000
33 |  |  | Building Demolition - Bids | 650000 |  | 650000 | 650000 | 0 | 0 | 650000 | 0 | 100% | 0 | 0 | 0 | 0% | 650000
|  |  | Pre-Redevelopment Phase | 998673 | 0 | 998673 | 998673 | 0 | 0 | 998673 | 0 | 100% | 130845.98 | 1000 | 131845.98 | 13.2% | 866827.02
100 |  |  | Environmental- OER Support Services- WCD | 5750 |  | 5750 | 5750 | 0 | 0 | 5750 | 0 | 100% | 0 | 0 | 0 | 0% | 5750
101 |  |  | Architecture- Construction Document Phase- SBLM | 275000 |  | 275000 | 275000 | 0 | 0 | 275000 | 0 | 100% | 0 | 0 | 0 | 0% | 275000
102 |  |  | Architecture- Bidding Phase- SBLM | 25000 |  | 25000 | 25000 | 0 | 0 | 25000 | 0 | 100% | 0 | 0 | 0 | 0% | 25000
103 |  |  | Architecture- Construction Administration Phase- SBLM | 90000 |  | 90000 | 90000 | 0 | 0 | 90000 | 0 | 100% | 0 | 0 | 0 | 0% | 90000
104 |  |  | Expediting Services- SBLM | 37400 |  | 37400 | 37400 | 0 | 0 | 37400 | 0 | 100% | 0 | 0 | 0 | 0% | 37400
105 |  |  | Geotech- Task 300- SOE & Underpinning- Mueser Rutledge | 56000 |  | 56000 | 56000 | 0 | 0 | 56000 | 0 | 100% | 0 | 0 | 0 | 0% | 56000
106 |  |  | Geotech- Task 400- Construction Phase-Mueser Rutledge | 26850 |  | 26850 | 26850 | 0 | 0 | 26850 | 0 | 100% | 0 | 0 | 0 | 0% | 26850
[8 empty] | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
|  |  | Redevelopment | 516000 | 0 | 516000 | 516000 | 0 | 0 | 516000 | 0 | 100% | 0 | 0 | 0 | 0% | 516000
200 |  |  | Con Edison Deposit | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 17160 | 0 | 17160 | 0% | -17160
201 |  |  | Utilities | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 64215.68 | 10114.32 | 74330 | 0% | -74330
202 |  |  | Steam Line/ Boiler Relocation- Professional Fees- SBLM | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 4357.96 | 0 | 4357.96 | 0% | -4357.96
203 |  |  | Steam Line/ Boiler Relocation- Construction Fees- TBD | 50000 |  | 50000 | 50000 | 0 | 0 | 50000 | 0 | 100% | 0 | 0 | 0 | 0% | 50000
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
|  |  | Utilities | 50000 | 0 | 50000 | 50000 | 0 | 0 | 50000 | 0 | 100% | 85733.64 | 10114.32 | 95847.96 | 191.7% | -45847.96
300 |  |  | Reimbursable- Mileage | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2709.04 | 484.92 | 3193.96 | 0% | -3193.96
301 |  |  | Misc Legal (DE State) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 300 | 0 | 300 | 0% | -300
302 |  |  | Consulting - East Gate | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 33225.8 | 15000 | 48225.8 | 0% | -48225.8
303 |  |  | Interest - Line of Credit | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 129588.88 | 33041.67 | 162630.55 | 0% | -162630.55
304 |  |  | Security - Summit | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2513.39 | 1034.31 | 3547.7 | 0% | -3547.7
305 |  |  | Computer Expenses/ Postage | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 513.07 | 145.32 | 658.39 | 0% | -658.39
306 |  |  | Accounting fees - Tax prep | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1683 | 0 | 1683 | 0% | -1683
|  |  | Overhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 170533.18 | 49706.22 | 220239.4 | 0% | -220239.4
400 |  |  | Marketing | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 13885 | 8328.12 | 22213.12 | 0% | -22213.12
401 |  |  | Marketing- Bud Event | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 20366.91 | 0 | 20366.91 | 0% | -20366.91
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0
|  |  | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 34251.91 | 8328.12 | 42580.03 | 0% | -42580.03
|  |  | GRAND TOTAL | 1983118 | 20007.62 | 2003125.62 | 1890437.62 | 0 | 0 | 1890437.62 | -112688 | 94.37% | 6029112.35 | 169640.93 | 6198753.28 | 327.9% | -4287966.12
Note on J13: dvenn: #'s highlighted in blue are based on GTL's current contract. Individual line items are estimates.

## Invoice Log
Rec'd by Developer | ID # | Draw # | Check # | Check Date | Date Submitted for Payment | Invoice # | Invoice Date | Invoice Amt | GL Code | Contractor | Services | Description | Additional Comments | Column2 | Column3
| 27 |  |  |  |  | 1508099 | 2015-09-30 | 27096 |  | ACQUIFER DRILLING & TESTING | Contractor- Drilling | Indoor/Outdoor Boring
| 4 | 1 |  |  |  | 12-CNY-45727 | 2012-11-30 | 88575.25 |  | ADVANTAGE TITLE |  | closing costs
| 4 | 1 |  |  |  | SSA-33516-15 | 2015-04-14 | 653.25 |  | ADVANTAGE TITLE |  | Zoning Lot Certifica
| 3 | 1 |  |  |  | 14685 | 2014-09-01 | 3000 |  | ARCHIDATA BUILDING SURVEYS, INC. |  | FieldSurvey/CAD 08-1
| 3 | 2 |  |  |  | 14801 | 2015-02-01 | 975 |  | ARCHIDATA BUILDING SURVEYS, INC. |  | FieldSurvey/CAD 08-1
| 4 | [6 empty] | 335 |  | Blades, Crout
| 4 | 1 |  |  |  | 09057363 | 2013-04-11 | 450 |  | BLUMBERG EXCELSIOR SVC, INC. |  | Legal Adv. Disb. 4/1
| 4 | 1 |  |  |  | 09348735 | 2013-10-09 | 139 |  | BLUMBERG EXCELSIOR SVC, INC. |  | Prof. Fees-Onyx31st
| 4 | 1 |  |  |  | 09349583 | 2013-11-06 | 139 |  | BLUMBERG EXCELSIOR SVC, INC. |  | DE Good StgCert.31st
| 300 | 1 |  |  |  | NYX31-062915 | 2015-06-29 | 41 |  | CARLOS RAMOS | Public transportatio | Public transportatio
| 300 | 1 |  |  |  | RAM-082615 | 2015-08-26 | 25.76 |  | CARLOS RAMOS | Misc. supplies | Misc. supplies
| 1 | 1 |  |  |  | 759330 | 2015-06-04 | 2607.51 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | 05-15 Easement RE Ta | 05-15 Easement RE Ta
| 1 | 1 |  |  |  | 760980 | 2015-07-06 | 1116.75 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | ZLDA- Ground Lease | ZLDA- Ground Lease
| 1 | 1 |  |  |  | 763180 | 2015-08-10 | 3857.65 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 3 |  |  |  | 767279 |  | 1608.3 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 3 |  |  |  | 769368 |  | 2587.5 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 3 | [5 empty] | 21923.9 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 759330 | 2015-06-04 | 2607.51 | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | Due Diligence Step 1
| 1 | 1 |  |  |  | 760980 | 2015-07-06 | 1116.75 | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | ZLDA Work
| 1 | 1 |  |  |  | 711843-r | 2013-01-04 | 10000 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Legal 12/12
| 1 | 1 |  |  |  | 711843-r | 2013-01-04 | 1436.57 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Legal 12/12
| 1 | 1 |  |  |  | 713319 | 2013-02-05 | 36191.62 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Onyx31-lgl 1/13
| 1 | 1 |  |  |  | 734050 | 2014-02-05 | 2034.65 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | legal 1/14
| 1 | 1 |  |  |  | 736006 | 2014-03-07 | 1643.75 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | 9 | Legal 2/14
| 1 | 1 |  |  |  | 742244 | 2014-07-08 | 131.25 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | 210W31st.St-6/14
| 1 | 1 |  |  |  | 748400 | 2014-11-05 | 15547.15 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Oct 2014 Legal 31st
| 1 | 1 |  |  |  | 752321 | 2015-01-09 | 12058.42 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Legal Work 11/14
| 1 | 1 |  |  |  | 752809 | 2015-02-03 | 21073.44 | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | Due Diligence Step 1
| 1 | 1 |  |  |  |  | 2015-02-03 |  | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | Ad-Hoc Step | Ground Lease
| 1 | 1 |  |  |  |  | 2015-02-03 |  |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Easement Docs/other
| 1 | 1 |  |  |  | 754643 | 2015-03-05 | 27106.65 | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | Due Diligence Step 1
| 1 | 1 |  |  |  | 754643 | 2015-03-05 |  | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | Ad-Hoc Step | Ground Lease
| 1 | 1 |  |  |  | 756470 | 2015-04-07 | 4884.13 | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | Due Diligence Step 1 | Ground Lease
| 1 | 1 |  |  |  | 757894 | 2015-05-07 | 2770.7 | Jon Hu | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA | Legal | Due Diligence Step 1
| 1 | 1 |  |  |  | REIMB |  | -38445.75 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 714922 | 2013-03-05 | 4133.22 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 716201 | 2013-04-03 | 19713.85 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 718235 | 2013-05-06 | 2525.02 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 719381 | 2013-06-04 | 123.75 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 721320 | 2013-07-03 | 1961.25 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 722841 | 2013-08-05 | 468.75 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 729075 | 2013-11-03 | 262.5 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 731561 | 2013-12-04 | 331.25 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA
| 1 | 1 |  |  |  | 750309 | 2014-12-02 | 17700.54 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Legal 31stSt Nov 201
| 1 | 1 |  |  |  | 743471 | 2014-08-05 | 6994.5 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | St.John Baptist-210-
| 1 | 1 |  |  |  | 754643 | 2015-03-05 | 20109.9 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Term agreements
| 1 | 1 |  |  |  | 756470 | 2015-04-07 | 4614.13 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | 03-15 title recrdngd
| 1 | 1 |  |  |  | 757894 | 2015-05-07 | 2020.45 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | Lgl 31st Street 4/30
| 1 | 1 |  |  |  | 737146R | 2014-04-03 | 3281.25 |  | COLE,SCHOTZ,MEISEL,FORMAN &LEO. PA |  | 3/15 legal work
| 200 | 1 |  |  |  | 00018-031915 | 2015-03-19 | 145 |  | CON EDISON |  | 437241176500018-S/D
| 200 | 1 |  |  |  | 01013-031615 | 2015-03-16 | 4455 |  | CON EDISON |  | 437241176201013-S/D
| 201 | 1 |  |  |  | 00018-022015 | 2015-02-20 | 80.95 |  | CON EDISON |  | 437241176500018-02/1
| 201 | 1 |  |  |  | 51224-022015 | 2015-02-20 | 11129.23 |  | CON EDISON |  | 6897751224 2/15
| 201 | 1 |  |  |  | 01013-031615 | 2015-03-16 | 418.61 |  | CON EDISON |  | 437241176201013-02/1
| 201 | 1 |  |  |  | 01013-031815 | 2015-03-18 | 1415.84 |  | CON EDISON |  | 437241176201013-4/15
| 201 | 1 |  |  |  | 00018-031915 | 2015-03-19 | 61.8 |  | CON EDISON |  | 437241176500018-03/1
| 201 | 1 |  |  |  | 51224-032015 | 2015-03-20 | 18889.42 |  | CON EDISON |  | 6897751224 3/15
| 201 | 1 |  |  |  | 01013-041615 | 2015-04-16 | 3110.86 |  | CON EDISON |  | 437241176201013-3/15
| 201 | 1 |  |  |  | 51224-042115 | 2015-04-21 | 5172.11 |  | CON EDISON |  | 6897751224 4/15
| 201 | 1 |  |  |  | 01013-051815 | 2015-05-18 | 1245.77 |  | CON EDISON |  | 437241176201013-05/1
| 201 | 1 |  |  |  | 51224-052715 | 2015-05-27 | 3948.09 |  | CON EDISON |  | 6897751224 5/15
| 201 | 1 |  |  |  | 01013-061815 | 2015-06-18 | 2109.47 |  | CON EDISON | 437241176201013-06/1 | 437241176201013-06/1
| 201 | 1 |  |  |  | 01013-061815 | 2015-06-18 | -1245.77 |  | CON EDISON | 437241176201013-06/1 | 437241176201013-06/1
| 201 | 1 |  |  |  | 01013-071715 | 2015-07-17 | 1141.43 |  | CON EDISON | 437241176201013-07/1 | 437241176201013-07/1
| 201 | 1 |  |  |  | 01013-081715 | 2015-08-17 | 1078.22 |  | CON EDISON | 437241176201013-08/1 | 437241176201013-08/1
| 201 | 1 |  |  |  | 51224-0515R | 2015-06-22 | 61.71 |  | CON EDISON | 6897751224 5/15Rebil | 6897751224 5/15Rebil
| 201 | 1 |  |  |  | 51224-062215 | 2015-06-22 | 4270.88 |  | CON EDISON | 6897751224 6/15 | 6897751224 6/15
| 201 | 1 |  |  |  | 51224-072315 | 2015-07-23 | 3525.63 |  | CON EDISON | 6897751224 7/15 | 6897751224 7/15
| 201 | 1 |  |  |  | 51224-081715 | 2015-08-17 | 3203.9 |  | CON EDISON | 6897751224 8/15 | 6897751224 8/15
| 201 | 3 |  |  |  | 01013-101615 | 2015-10-16 | 1022.91 |  | CON EDISON
| 201 | 3 |  |  |  | 51224-110915 | 2015-11-09 | 3544.15 |  | CON EDISON
| 201 | 3 |  |  |  | 1013-11/15 | 2015-11-17 | 1552.43 |  | CON EDISON
| 201 | 3 |  |  |  | 51224-11/15 | 2015-11-23 | 3972.06 |  | CON EDISON
| 4 | 1 |  |  |  | 2014-OE0305 | 2014-03-05 | 4950 |  | CONFIDENTIAL SECURITY & |  | Investigation Svcs
| 4 | 1 |  |  |  | 2014-OE0415 | 2014-04-15 | 550 |  | CONFIDENTIAL SECURITY & |  | Investigation Svcs
| 303 | 1 |  |  |  | 00100-081415 | 2015-08-14 | 16855.15 |  | CONNECT ONE BANK | 8-15 interest | 8-15 interest
| 303 | 1 |  |  |  | ONX31-071615 | 2015-07-16 | 12456.52 |  | CONNECT ONE BANK | 7/15 interest | 7/15 interest
| 303 | 1 |  |  |  | reserve |  | 75000 |  | CONNECT ONE BANK |  | interest reserve
| 303 | 2 |  |  |  |  | 2015-10-01 | 16250 |  | CONNECT ONE BANK
| 303 | 3 |  |  |  | 11/1/15 |  | 16791.67 |  | CONNECT ONE BANK
| 303 | 3 |  |  |  | 12/1/15 |  | 16250 |  | CONNECT ONE BANK
| 200 | 1 |  |  |  | 51224-depos | 2015-02-20 | 12560 |  | Consolidated Edison Company of NY |  | 68977-51224
| 4 | 1 |  |  |  | 5266586-2012 | 2013-04-26 | 250 |  | DELAWARE SECRETARY OF STATE |  | 2012 DE Tax
| 4 | 1 |  |  |  | 5270623-2013 | 2014-03-31 | 250 |  | DELAWARE SECRETARY OF STATE |  | Bluestone 31st DE13
| 4 | 1 |  |  |  | 66586-050214 | 2014-05-02 | 250 |  | DELAWARE SECRETARY OF STATE |  | DE 2013 Fee
| 4 | 1 |  |  |  | 66586-040715 | 2015-04-07 | 300 |  | DELAWARE SECRETARY OF STATE |  | DE Tax
| 4 | 1 |  |  |  | 5270618-14 | 2015-04-09 | 300 |  | DELAWARE SECRETARY OF STATE |  | OnyxEP31st
| 301 | 1 |  |  |  | 570623-14 | 2015-03-31 | 300 |  | DELAWARE SECRETARY OF STATE |  | 2014 DE tax
| 302 | 1 |  |  |  | 0000006 | 2015-06-12 | 3225.8 |  | EAST GATE REAL ESTATE ADVISORS LLC |  | 3/15 pro-ration
| 302 | 1 |  |  |  | 0000007 | 2015-06-12 | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC |  | 4/15 consultant
| 302 | 1 |  |  |  | 0000008 | 2015-06-12 | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC |  | 5/15 consultant
| 302 | 1 |  |  |  | 0000009 | 2015-06-12 | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC | 6/15 consultant | 6/15 consultant
| 302 | 1 |  |  |  | 0000013 | 2015-07-09 | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC | 7/15 consultant | 7/15 consultant
| 302 | 1 |  |  |  | 15 | 2015-08-03 | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC
| 302 | 1 |  |  |  | 16 | 2015-09-08 | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC
| 302 | 3 | [5 empty] | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC
| 302 | 3 | [5 empty] | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC
| 302 | 3 | [5 empty] | 5000 |  | EAST GATE REAL ESTATE ADVISORS LLC
| 4 | 1 |  |  |  | X2016-091214 | 2014-09-12 | 46.39 |  | EVAN DREMLUCK |  | Meals Exp.-9/10
| 4 | 1 |  |  |  | X2016-091214 | 2014-09-12 | 40 |  | EVAN DREMLUCK |  | Mileage Exp.-9/10
| 4 | 1 |  |  |  | 7354612 | 2014-07-30 | 1530 |  | FTI CONSULTING, INC. |  | 2013 tax prep
| 306 | 1 |  |  |  | 7381171 | 2015-05-31 | 1683 |  | FTI CONSULTING, INC. | 2014 Tax Return Prep | 2014 Tax Return Prep
| 3 | 1 |  |  |  | 452232 | 2013-12-28 | 4815 |  | GENSLER ARCHITECTURE DESIGN |  | Dec 2013 Architect
| 3 | 1 |  |  |  | 457609 | 2014-02-13 | 7931 |  | GENSLER ARCHITECTURE DESIGN |  | Zoning Analysis Prog
| 3 | 1 |  |  |  | 472733 | 2014-05-15 | 993.76 |  | GENSLER ARCHITECTURE DESIGN |  | Zoning Analysis-4/14
| 3 | 1 |  |  |  | 493040 | 2014-09-12 | 341.87 |  | GENSLER ARCHITECTURE DESIGN |  | Retail Base/Hotel-Pr
| 3 | 1 |  |  |  | 501290 | 2014-10-16 | 12016.46 |  | GENSLER ARCHITECTURE DESIGN |  | Facade Redesign&Rend
| 3 | 1 |  |  |  | 507346 | 2014-12-18 | 341.81 |  | GENSLER ARCHITECTURE DESIGN |  | Retail/HotelRender
| 3 | 1 |  |  |  | 512289 | 2015-01-15 | 490 | Jon Hu | GENSLER ARCHITECTURE DESIGN | Architectural | Ad-Hoc Step | 1-hr: $170/hr + 2-hrs: $160/hr
| 3 | 1 |  |  |  | 512290 | 2015-01-15 | 148.06 | Jon Hu | GENSLER ARCHITECTURE DESIGN | Architectural | Ad-Hoc Step | Reproduction
| 3 | 1 |  |  |  | 512292 | 2015-01-15 | 161.83 | Jon Hu | GENSLER ARCHITECTURE DESIGN | Architectural | Ad-Hoc Step | Add'l Services for ZLDA & ADA Egress
| 3 | 1 |  |  |  | 518700 | 2015-02-12 | 512.52 | Jon Hu | GENSLER ARCHITECTURE DESIGN | Architectural | Ad-Hoc Step | 4-hrs: $125/hr
| 3 | 1 |  |  |  | 524608 | 2015-03-19 | 1657.8 |  | GENSLER ARCHITECTURE DESIGN |  | Planning&DocsBSA/DOB
| 3 | 1 |  |  |  | 507348 | 2014-12-18 | 247.91 |  | GENSLER ARCHITECTURE DESIGN |  | Facade Design/Render
| 3 | 1 |  |  |  | 507349 | 2014-12-18 | 10950 |  | GENSLER ARCHITECTURE DESIGN |  | Planning&DocsBSA/DOB
| 3 | 1 |  |  |  | 512289 | 2015-01-15 | 490 |  | GENSLER ARCHITECTURE DESIGN |  | Retail/HotelRender
| 3 | 1 |  |  |  | 512290 | 2015-01-15 | 148.06 |  | GENSLER ARCHITECTURE DESIGN |  | Reimbursables 12/14
| 3 | 1 |  |  |  | 512292 | 2015-01-15 | 161.83 |  | GENSLER ARCHITECTURE DESIGN |  | Assessmnt of Structu
| 3 | 1 |  |  |  | 518700 | 2015-02-12 | 512.52 |  | GENSLER ARCHITECTURE DESIGN |  | Planning Docs 1/15
| 3 | 1 |  |  |  | 501297 | 2014-10-16 | 4115 |  | GENSLER ARCHITECTURE DESIGN |  | Assmt for Retail Con
| 3 | 1 |  |  |  | 503471 | 2014-11-13 | 377.87 |  | GENSLER ARCHITECTURE DESIGN |  | Reimbursable Exp 10-
| 3 | 1 |  |  |  | 504575 | 2014-11-13 | 8052.5 |  | GENSLER ARCHITECTURE DESIGN |  | Assmt of structure f
| 3 | 1 |  |  |  | 493041 | 2014-09-12 | 4300 |  | GENSLER ARCHITECTURE DESIGN |  | Facade Redesign/Rend
| 3 | 1 |  |  |  | 493092 | 2014-09-12 | 4840 |  | GENSLER ARCHITECTURE DESIGN |  | Assmt. for Existing
| 3 | 1 |  |  |  | 472734 | 2014-05-15 | 7000 |  | GENSLER ARCHITECTURE DESIGN |  | Res.Scenario Dev.4/1
| 3 | 1 |  |  |  | 478944 | 2014-06-19 | 7524.31 |  | GENSLER ARCHITECTURE DESIGN |  | RB/Hotel-ConceptRend
| 3 | 1 |  |  |  | 461648 | 2014-03-20 | 5864.5 |  | GENSLER ARCHITECTURE DESIGN |  | Zoning Analysis Prog
| 3 | 1 |  |  |  | 467903 | 2014-04-17 | 615 |  | GENSLER ARCHITECTURE DESIGN |  | Zoning Analysis Prog
| 2 | 1 |  |  |  | 3920587 | 2015-05-18 | 7013.74 | Jon Hu | GREENBERG TRAURIG, LLP | Legal |  | Zoning Conference Calls
| 2 | 1 |  |  |  | 3614170 | 2014-03-21 | 10984.5 |  | GREENBERG TRAURIG, LLP |  | Zoning legal 2/14
| 2 | 1 |  |  |  | 3632560 | 2014-04-15 | 9642.5 |  | GREENBERG TRAURIG, LLP |  | 210West31stSt-Zoning
| 2 | 1 |  |  |  | 3674603 | 2014-06-10 | 3667 |  | GREENBERG TRAURIG, LLP |  | 31stSt Legal-Zoning
| 2 | 1 |  |  |  | 3701398 | 2014-07-21 | 3570 |  | GREENBERG TRAURIG, LLP |  | zoning 6/14
| 2 | 1 |  |  |  | 3833468 | 2015-01-26 | 6456.5 | Jon Hu | GREENBERG TRAURIG, LLP | Legal | Due Diligence Step 1
| 2 | 1 |  |  |  | 3833468 | 2015-01-26 | 6456.5 | Jon Hu | GREENBERG TRAURIG, LLP | Legal | Ad-Hoc Step | Zoning
| 2 | 1 |  |  |  | 3833468 | 2015-01-26 | 6456.5 |  | GREENBERG TRAURIG, LLP |  | 12-14 Legal-Zoning
| 2 | 1 |  |  |  | 3875035 | 2015-03-27 | 5223.5 | Jon Hu | GREENBERG TRAURIG, LLP | Legal | Due Diligence Step 1 | Zoning: Legal services through 2/28/2015
| 2 | 1 |  |  |  | 3899199 | 2015-04-24 | 9817.5 | Jon Hu | GREENBERG TRAURIG, LLP | Legal | Due Diligence Step 1 | Zoning
| 2 | 1 |  |  |  | 3940053 | 2015-06-09 | 1782.02 | Jon Hu | GREENBERG TRAURIG, LLP | Legal | Zoning Work
| 2 | 1 |  |  |  | 3850801 | 2015-02-19 | 14230 |  | GREENBERG TRAURIG, LLP |  | 01-15 Zoning Easemts
| 2 | 1 |  |  |  | 3722208 | 2014-08-22 | 8549 |  | GREENBERG TRAURIG, LLP |  | 31stSt Legal-Zoning
| 2 | 1 |  |  |  | 3743599 | 2014-09-24 | 8018 |  | GREENBERG TRAURIG, LLP |  | 31stSt Legal- Zoning
| 2 | 1 |  |  |  | 3760700 | 2014-10-13 | 10225 |  | GREENBERG TRAURIG, LLP |  | 31stSt Legal-Zoning
| 2 | 1 |  |  |  | 3785526 | 2014-11-13 | 21865.2 |  | GREENBERG TRAURIG, LLP |  | 31stSt Legal-Zoning
| 2 | 1 |  |  |  | 3801477 | 2014-12-05 | 18702.55 |  | GREENBERG TRAURIG, LLP |  | 31stSt Legal-Zoning
| 2 | 1 |  |  |  | 3653395 | 2014-05-13 | 12519.5 |  | GREENBERG TRAURIG, LLP |  | 210West31stSt-Zoning
| 2 | 1 |  |  |  | 3873035 | 2015-03-23 | 5223.5 |  | GREENBERG TRAURIG, LLP
| 2 | 1 |  |  |  | 3899199 | 2015-04-24 | 9817.5 |  | GREENBERG TRAURIG, LLP
| 2 | 1 |  |  |  | 3940053 | 2015-06-06 | 1782.02 |  | GREENBERG TRAURIG, LLP
| 2 | 1 |  |  |  | 3969829 | 2015-07-27 | 6826.66 |  | GREENBERG TRAURIG, LLP
| 5 | 2 |  |  |  | 3969829 | 2015-06-27 | 6826.66 |  | GREENBERG TRAURIG, LLP
| 4 | 1 |  |  |  | 3045702 | 2015-03-18 | 6810.73 |  | HUB INTERNATIONAL NORTHEAST-TRUST |  | NYFIF 2/1-10/5/15
| 4 | 3 | [5 empty] | 6949 |  | HUB INTERNATIONAL NORTHEAST-TRUST
| 400 | 1 |  |  |  | ICSC-042415 | 2015-04-24 | 197 |  | ICSC |  | ICSC-12/15
| 300 | 2 |  |  |  | 204516 | 2015-02-06 | 64.47 |  | Impulse Courier Services Inc | Messenger service 7/15
| 8 | 3 |  |  |  | Inc-9212015 |  | 3400 |  | Incinia Contrating | Contractor- Environemtal Abatement | Asbestos Abatement inside Church
| 4 | 1 |  |  |  | 29832 | 2014-12-25 | 375 |  | INTERNATIONAL COUNCIL OF |  | NY Show 12/8/14
| 26 | 1 |  |  |  | 1 | 2015-06-05 | 4500 |  | J Coffey | Contractor- Drilling | Test Pit- Indoor- Basement
| 26 | 1 |  |  |  | 01-092115 | 2015-10-02 | 7450 |  | J Coffey | Contractor- Drilling | Test Pit-Outdoor- Courtyard Excavation
| 300 | 1 |  |  |  | X2016-020415 | 2015-02-04 | 23.75 |  | JEFFREY FULLER |  | Metro card
| 300 | 1 |  |  |  | X2016-0215B | 2015-02-04 | 40 |  | JEFFREY FULLER |  | Mileage JF 2/15
| 300 | 1 |  |  |  | X2016-020415 | 2015-02-04 | 124.55 |  | JEFFREY FULLER |  | Catering
| 300 | 1 |  |  |  | X2016-020415 | 2015-02-04 | 1257.51 |  | JEFFREY FULLER |  | Lock changes
| 300 | 1 |  |  |  | NYX31-080615 | 2015-08-06 | 173.37 |  | JEFFREY FULLER | Meeting lunch | Meeting lunch
| 300 | 1 |  |  |  | NYX31-080615 | 2015-08-06 | 77.85 |  | JEFFREY FULLER | Transportation | Transportation
| 300 | 1 |  |  |  | NYX31-082615 | 2015-08-26 | 28 |  | JEFFREY FULLER | Parking | Parking
| 300 | 1 |  |  |  | NYX31-082615 | 2015-08-26 | 44.62 |  | JEFFREY FULLER | Public transportatio | Public transportatio
| 4 | 1 |  |  |  | X2016-010815 | 2015-01-08 | 5766.41 |  | JOHN S LAVALLEY |  | ICSC Conference
| 4 | 1 |  |  |  | X2016-010815 | 2015-01-08 | 158.29 |  | JOHN S LAVALLEY |  | Presentation Materia
| 4 | 1 |  |  |  | X2016-010815 | 2015-01-08 | 3928.62 |  | JOHN S LAVALLEY |  | Travel Exp.
| 401 | 1 |  |  |  | NYX31-080515 | 2015-08-05 | 1600 |  | JONATHAN BANQUER DAVIS | Equipment rental | Equipment rental | Budweiser Event
| 401 | 1 |  |  |  | NYX31-072415 | 2015-07-24 | 1600 |  | JONATHAN BANQUER DAVIS | Equipment rental | Equipment rental | Budweiser Event
| 300 | 1 |  |  |  | NYX31-040715 | 2015-04-07 | 194.32 |  | MICHELLE SZCZESNY |  | Mileage MS 2/15
| 300 | 1 |  |  |  | NYX31-041015 | 2015-04-10 | 49 |  | MICHELLE SZCZESNY |  | Tolls
| 300 | 1 |  |  |  | NYX31-041015 | 2015-04-10 | 30 |  | MICHELLE SZCZESNY |  | Metrocard
| 300 | 1 |  |  |  | NYX31-041015 | 2015-04-10 | 14.01 |  | MICHELLE SZCZESNY |  | Keys
| 300 | 1 |  |  |  | NYX31-041015 | 2015-04-10 | 147.47 |  | MICHELLE SZCZESNY |  | Mileage 3/2015
| 300 | 1 |  |  |  | NYX31-040715 | 2015-04-07 | 53.71 |  | MICHELLE SZCZESNY |  | R&M Supplies 2/15
| 300 | 3 | [5 empty] | 295.27 |  | MICHELLE SZCZESNY
| 3 | 1 |  |  |  | 20131500 | 2013-06-20 | 150 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Easements- Revised
| 3 | 1 |  |  |  | 15P0128 | 2015-02-06 | 500 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Eastment & Encroachment w/ Descriptions
| 3 | 1 |  |  |  | MONTROSE1 | 2015-02-19 | 1900 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Deposit- Arch Survey
| 3 | 1 |  |  |  | 20150319 | 2015-02-17 | 500 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Easements- Revised
| 3 | 1 |  |  |  | 20151195 | 2015-06-16 | 5400 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Metes & Bounds Description
| 3 | 1 |  |  |  | 20151196 | 2015-06-22 | 200 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Legal Description for Lot 26 (Church)
| 12 | 1 |  |  |  | 20150465 | 2015-03-10 | 1900 | Jon Hu | MONTROSE SURVEYING CO, LLP. | Surveyor | Balance- Arch Survey | Total Fee: $3,800 / Already Paid: $1,900
| 12 | 1 |  |  |  | 20150465 | 2015-03-10 | 1900 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Utility Site Survey- Side Yard Platform | Requested by SBLM
| 21 | 3 |  |  |  | MONT101415 | 2015-10-14 | 1000 |  | MONTROSE SURVEYING CO, LLP. | Surveyor | Elevation Take-Offs
| 400 | 1 |  |  |  | 1375 | 2015-04-28 | 3266.25 | Jon Hu | MOTIONLOFT | Market DD | 2 Trackers to track pedestrian traffic
| 400 | 1 |  |  |  | 1375 | 2015-04-28 | 3266.25 |  | MOTIONLOFT | Survey Fees 4/28/15 | Survey Fees 4/28/15
| 24 | 1 |  |  |  | 12417-2 | 2015-05-19 | 10734.56 | Jon Hu | MUESER RUTLEDGE CONSULTING ENG. | Geotechnical Engineer | Task 100- Pre-Construction Survey & TP | Engineering Services; Previously invoiced $264.48 - Total due: $10,999.04
| 24 | 1 |  |  |  | 12417-1 | 2015-04-16 | 264.48 |  | MUESER RUTLEDGE CONSULTING ENG. | Geotechnical Engineer | Task 100- Pre-Construction Survey & TP
| 24 | 1 |  |  |  | 12417-4 (i) | 2015-09-30 | 6344.08 |  | MUESER RUTLEDGE CONSULTING ENG. | Geotechnical Engineer | Task 100- Pre-Construction Survey & TP
| 24 | 1 |  |  |  | 12417-3 | 2015-06-29 | 3988.98 |  | MUESER RUTLEDGE CONSULTING ENG. | Geotechnical Engineer | Task 100- Pre-Construction Survey & TP
| 25 | 1 |  |  |  | 12417-4 (ii) | 2015-09-30 | 5499.55 |  | MUESER RUTLEDGE CONSULTING ENG. | Geotechnical Engineer | Task 200- Boring Program
| 25 |  |  |  |  | 12417-5 | 2015-10-21 | 17759.57 |  | MUESER RUTLEDGE CONSULTING ENG. | Geotechnical Engineer | Task 200- Boring Program
| 25 |  |  |  |  | 12417-6 | 2015-11-19 | 2758.3 |  | MUESER RUTLEDGE CONSULTING ENG. | Geotechnical Engineer | Task 200- Boring Program
| 300 | 3 | [5 empty] | 21 |  | NICOLE VASQUEZ
| 7 | 1 |  |  |  | 2158738 | 2015-07-16 | 3502 |  | NY ENVIRONMENTAL & ANALYTICAL | Environmental Prof. | Environmental Report
| 11 | 1 |  |  |  | OER1 | 2015-07-14 | 375 |  | NYC DEPARTEMENT OF | OER-Church Stair Rev | OER-Church Stair Rev
| 201 | 1 |  |  |  | 91001-042515 | 2015-04-25 | 929.98 |  | NYC WATER BOARD |  | 4000958991001 4/15
| 201 | 1 |  |  |  | 79001-062215 | 2015-06-22 | 1006.22 |  | NYC WATER BOARD | 00001155479001 6/15 | 00001155479001 6/15
| 201 | 1 |  |  |  | 91001-072515 | 2015-07-25 | 174.38 |  | NYC WATER BOARD | 4000958991001 7/15 | 4000958991001 7/15
| 201 | 2 |  |  |  | 79001-092215 | 2015-09-22 | 1042.01 |  | NYC WATER BOARD
| 201 | 3 |  |  |  | 91001-102415 |  | 22.77 |  | NYC WATER BOARD
| 4 | 1 |  |  |  | 146891 | 2014-05-01 | 13.02 |  | ONYX MANAGEMENT GROUP, LLC |  | Overnight Chgs.
| 305 | 1 |  |  |  | 168211 | 2015-03-18 | 27.16 |  | ONYX MANAGEMENT GROUP, LLC |  | Postage 2/15
| 305 | 1 |  |  |  | 170037 | 2015-04-27 | 28.54 |  | ONYX MANAGEMENT GROUP, LLC |  | MS Cell 1/14-2/13/15
| 305 | 1 |  |  |  | 170037 | 2015-04-27 | 23.26 |  | ONYX MANAGEMENT GROUP, LLC |  | MS Cell 2/14-3/13/15
| 305 | 1 |  |  |  | 170037 | 2015-04-27 | 67.22 |  | ONYX MANAGEMENT GROUP, LLC |  | Postage 3/7-4/11/15
| 305 | 1 |  |  |  | 173952 | 2015-07-14 | 131.05 |  | ONYX MANAGEMENT GROUP, LLC | Avid fees 2014 | Avid fees 2014
| 305 | 1 |  |  |  | 174623 | 2015-07-27 | 59.44 |  | ONYX MANAGEMENT GROUP, LLC | Avid Fees 1Q15 | Avid Fees 1Q15
| 305 | 1 |  |  |  | 174623 | 2015-07-27 | 94.79 |  | ONYX MANAGEMENT GROUP, LLC | Avid Fees 2Q15 | Avid Fees 2Q15
| 305 | 1 |  |  |  | 174623 | 2015-07-27 | 23.23 |  | ONYX MANAGEMENT GROUP, LLC | R&M Supplies 6/15 | R&M Supplies 6/15
| 305 | 1 | [5 empty] | 58.38 |  | ONYX MANAGEMENT GROUP, LLC |  | postage
| 305 | 3 | [5 empty] | 62.87 |  | ONYX MANAGEMENT GROUP, LLC
| 400 | 1 |  |  |  | 174623 | 2015-07-27 | 4373 |  | ONYX MANAGEMENT GROUP, LLC | ICSC NY Conference | ICSC NY Conference
| 201 | 1 |  |  |  | 15360 | 2015-04-10 | 1444.94 |  | PARKVIEW PLUMBING & HEATING, INC. |  | Cap Gas Main Line
| 300 | 1 |  |  |  | 0MACQ-040915 | 2015-04-09 | 81.36 |  | PAULA PANGILINAN |  | Mileage
| 300 | 1 |  |  |  | NYX31-042215 | 2015-04-22 | 154.29 |  | PAULA PANGILINAN |  | Mileage PP 1/15-4/15
| 300 | 1 |  |  |  | NYX31-061315 | 2015-06-13 | 8 |  | PAULA PANGILINAN | Train fare | Train fare
| 300 | 2 |  |  |  |  | 2015-09-28 | 60 |  | PAULA PANGILINAN
| 300 | 3 | [5 empty] | 168.65 |  | PAULA PANGILINAN
| 4 | 1 |  |  |  | ONX31-123113 | 2013-12-31 | 14704.28 |  | PHALANX FUND II, LP |  | Legal/Prof Reimb PX2
| 5 | 1 |  |  |  | 31OP-0813 | 2013-07-15 | 20833 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#5
| 5 | 1 |  |  |  | OPT-0913 | 2013-09-01 | 20833 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#6
| 5 | 1 |  |  |  | OPT-10/13 | 2013-09-30 | 20833 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#7
| 5 | 1 |  |  |  | OPT-10/13A | 2013-10-01 | 18334 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#7-Additional
| 5 | 1 |  |  |  | OPT831-11/13 | 2013-10-31 | 39167.01 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#8-Additional
| 5 | 1 |  |  |  | OPT-12/13 | 2013-11-27 | 39167.01 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#9-Contract De
| 5 | 1 |  |  |  | OPT10-1/14 | 2013-12-31 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#10-Contract D
| 5 | 1 |  |  |  | OPT11-2/14 | 2014-02-01 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#11-Contract D
| 5 | 1 |  |  |  | OPT12-3/14 | 2014-03-04 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#12-Contract D
| 5 | 1 |  |  |  | OPT13-04/14 | 2014-04-08 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#13-Contract D
| 5 | 1 |  |  |  | OPT14-5/14 | 2014-05-01 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#13-Contract D
| 5 | 1 |  |  |  | OPT15-6/14 | 2014-05-30 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#15-Contract D
| 5 | 1 |  |  |  | OPT-16-7/14 | 2014-06-30 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#16-Contract D
| 5 | 1 |  |  |  | OPT-17-8/14 | 2014-07-30 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#17-Contract D
| 5 | 1 |  |  |  | OPT-18-9/14 | 2014-08-26 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#18-Contract D
| 5 | 1 |  |  |  | OPT-19-10/14 | 2014-10-01 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#19-Contract D
| 5 | 1 |  |  |  | OPT-20-11/14 | 2014-10-28 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#20-Contract D
| 5 | 1 |  |  |  | OPT-21-12/14 | 2014-12-01 | 39167 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#21-Contract D
| 5 | 1 |  |  |  | 022615 | 2015-02-26 | 1000000 |  | PROVINCE OF ST MARY CAPUCHIN ORDER |  | Option#22-Contract D
| 5 | 1 |  |  |  | none-072715 | 2015-07-27 | 250621.56 |  | PROVINCE OF ST MARY CAPUCHIN ORDER | Delivery of Possessi | Delivery of Possessi | paid from escrow
| 5 | 1 |  |  |  | none-072715 | 2015-07-27 | 1749378.44 |  | PROVINCE OF ST MARY CAPUCHIN ORDER | Delivery of Possessi | Delivery of Possessi
| 5 | 1 |  |  |  | 31OP-0613 | 2013-05-23 | 1041.64 |  | RUSKIN MOSCOU FALTISCHECK P.C. |  | Onyx Pmt3-Onyx 31
| 5 | 1 |  |  |  | 31OP-0713 | 2013-07-01 | 20833 |  | RUSKIN MOSCOU FALTISCHECK P.C. |  | 7/13 Optn Pymt
| 4 | 1 |  |  |  | 6100435 | 2014-07-17 | 5832 |  | RUSKIN MOSCOU FALTISCHECK P.C. |  | GrdLse Legal 01 to 0
| 5 | 1 |  |  |  | 31OP-0613 | 2013-05-23 | 2604.13 |  | RUSKIN MOSCOU FALTISCHECK P.C. |  | OP Pmt3-Onyx 31 Blue
| 5 | 1 |  |  |  | 31OP-0613 | 2013-05-23 | 10416.5 |  | RUSKIN MOSCOU FALTISCHECK P.C. |  | OP Pmt3-Onyx 31 LMB
| 5 | 1 |  |  |  | 31OP-0613 | 2013-05-23 | 6770.73 |  | RUSKIN MOSCOU FALTISCHECK P.C. |  | OP Pmt3-Onyx 31 Fund
| 3 | 1 |  |  |  | 13-013-01 | 2013-03-14 | 1570 |  | S&L ARCHITECTURE STUDIO, LLC |  | Arch Fees 3/13
| 3 | 1 |  |  |  | 13-013-02 | 2013-06-10 | 2375 |  | S&L ARCHITECTURE STUDIO, LLC |  | Archt Fee-6/10/13
| 3 | 1 |  |  |  | 13-013-03 | 2013-06-18 | 125 |  | S&L ARCHITECTURE STUDIO, LLC |  | Easement Study
| 9 | 1 |  |  |  | SBLM001 | 2015-02-19 | 4250 |  | SBLM ARCHITECTS, PC | Architecture Services | Deposit- Side Yard Church Platform
| 9 | 1 |  |  |  | 0042944 | 2015-04-10 | 4250 |  | SBLM ARCHITECTS, PC | Architecture Services | Balance- Side Yard Church Platform
| 13 | 2 |  |  |  | 0044669 | 2015-09-18 | 2580 |  | SBLM ARCHITECTS, PC | Architecture Services | Temp Signage
| 13 | 1 |  |  |  | 0042967 | 2015-04-13 | 5000 | Jon Hu | SBLM ARCHITECTS, PC | Architecture Services | Drape Design
| 13 |  |  |  |  | 0044669 | 2015-09-18 | 2580 |  | SBLM ARCHITECTS, PC | Architecture Services | Drape Design
| 13 |  |  |  |  | 0044960 | 2015-10-16 | 2296.89 |  | SBLM ARCHITECTS, PC | Architecture Services | Drape Design- Structural Engineering
| 13 |  |  |  |  | 0045697 | 2015-12-18 | 360 |  | SBLM ARCHITECTS, PC | Architecture Services | Drape Design- Structural Engineering
| 15 | 1 |  |  |  | 0041698 | 2014-12-12 | 10000 |  | SBLM ARCHITECTS, PC | Architecture Services | 11-14 architect
| 22 | 1 |  |  |  | 0044105 | 2015-07-23 | 15002.16 |  | SBLM ARCHITECTS, PC | Architecture Services | Schematic Phase
| 22 | 1 |  |  |  | 44352 | 2015-08-21 | 7621.22 |  | SBLM ARCHITECTS, PC | Architecture Services | Schematic Phase
| 22 |  |  |  |  | 0045696 | 2015-12-18 | 29.72 |  | SBLM ARCHITECTS, PC | Architecture Services | Schematic Phase- Reimbursables
| 202 | 2 |  |  |  | 0044668 | 2015-09-18 | 1618.98 |  | SBLM ARCHITECTS, PC | Architecture Services | Boiler Study
| 202 | 1 |  |  |  | 44353 | 2015-08-21 | 1120 |  | SBLM ARCHITECTS, PC | Architecture Services | Steam Boiler Study
| 202 |  |  |  |  | 0044668 | 2015-09-18 | 1618.98 |  | SBLM ARCHITECTS, PC | Architecture Services | Steam Boiler Study
| 400 | 1 |  |  |  | 11933 | 2015-05-19 | 382.5 | Jon Hu | Sensory Interactive | Marketing Consultant | Task 1 | Consultant Reimbursement
| 400 | 1 |  |  |  | 11932 | 2015-05-19 | 2400 |  | Sensory Interactive | Marketing Consultant | Signage Consultants
| 15 | 3 | [5 empty] | 7100 |  | Slifestories | Signage Consultant | LaValley coordinated
| 305 | 3 | [5 empty] | 59.98 |  | STAMPS.COM
| 304 | 1 |  |  |  | 4349056 | 2015-06-20 | 165.49 |  | SUMMIT SECURITY SERVICES INC. | Security6/14-6/20/15 | Security6/14-6/20/15
| 304 | 1 |  |  |  | 4349470 | 2015-06-27 | 330.98 |  | SUMMIT SECURITY SERVICES INC. | Security6/21-6/27/15 | Security6/21-6/27/15
| 304 | 1 |  |  |  | 4350510 | 2015-07-04 | 330.98 |  | SUMMIT SECURITY SERVICES INC. | Security 6/28-7/4/15 | Security 6/28-7/4/15
| 304 | 1 |  |  |  | 4350988 | 2015-07-11 | 165.49 |  | SUMMIT SECURITY SERVICES INC. | Security7/5-7/11/15 | Security7/5-7/11/15
| 304 | 1 |  |  |  | 4351654 | 2015-07-25 | 186.18 |  | SUMMIT SECURITY SERVICES INC. | Security7/19-7/25/15 | Security7/19-7/25/15
| 304 | 1 |  |  |  | 4352491 | 2015-08-01 | 1044.66 |  | SUMMIT SECURITY SERVICES INC. | Security 7/26-8/1/15 | Security 7/26-8/1/15
| 304 | 1 |  |  |  | 4353056 | 2015-08-08 | 289.61 |  | SUMMIT SECURITY SERVICES INC. | Security 8/2-8/8/15 | Security 8/2-8/8/15
| 304 | 3 |  |  |  | 435773 |  | 1034.31 |  | SUMMIT SECURITY SERVICES INC.
| 400 | 3 |  |  |  | 15013 | 2015-11-09 | 8300 |  | Terry Weems | Motion Graphics & Animation Freelancer | Budweiser & Heineken Video
| 300 | 1 |  |  |  | NYX31-042415 | 2015-04-24 | 16 |  | TIERRA JAMES |  | NJ Transit
| 3 | 1 |  |  |  | 124609 | 2014-12-22 | 10059.65 |  | TPG ARCHITECTURE, LLP |  | FacadeStudyReimburse
| 3 | 1 |  |  |  | 125459 | 2015-02-23 | 21.2 |  | TPG ARCHITECTURE, LLP |  | FacadeStudyReimburse
| 305 | 3 | [5 empty] | 22.47 |  | UPS
| 14 | 1 |  |  |  | 4633 | 2015-05-13 | 15188.06 |  | VariDirect Solutions, Inc. | Sign Vendor | Install Banner on Façade | Newmark handled coordination
| 10 | 3 |  |  |  | 210-A-003.1 | 2015-09-11 | 55455.57 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Side Yard Church Platform App #1
| 10 |  |  |  |  | 210-A-003.2 | 2015-11-05 | 76427.39 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Side Yard Church Platform App #2
| 10 |  |  |  |  | 210-A-003.F | 2015-11-30 | 14653.66 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Side Yard Church Platform App #3- Final
| 16 | 1 |  |  |  | 210-A-002.1 | 2015-04-24 | 117307.19 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Minor Demo & Clean up | Sub-contractor: Kevin Ward ($25K)
| 16 | 1 |  |  |  | 210-A-002.F | 2015-05-27 | 13034.13 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Minor Demo & Clean up | Sub-contractor: Kevin Ward ($25K)
| 16 | 2 |  |  |  | 6512 | 2015-09-24 | 2690.1 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | General Conditions | Project Superintendent
| 18 |  |  |  |  | 6962 | 2015-12-07 | 4531.54 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Clean-Up / Secure Building | Closed 31st Street Church Access
| 18 |  |  |  |  | 7023 | 2015-12-21 | 18718 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | De-branding | Removal of Cross, Jesus Statue, & Church Letters
| 26 |  |  |  |  | 6961 | 2015-12-07 | 9918.14 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Interior Test Pits | Additional Services
| 28 | 2 |  |  |  | 6506 | 2015-09-22 | 6829.22 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | General Conditions | Project Manager, Field Manager, Sr. Project Executive
| 401 | 2 |  |  |  | 6507 | 2015-09-22 | 9318.06 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Prep/Clean-Up for Marketing | Budweiser Event
| 401 | 2 |  |  |  | 6508 | 2015-09-22 | 7848.85 |  | VERICON CONSTRUCTION COMPANY, LLC | General Contractor | Roof Platform for Marketing | Budweiser Event
| 400 | 3 | [5 empty] | 28.12 |  | VTS | View The Space | Updates on Marketing Activity
| 6 | 1 |  |  |  | none-083013 | 2013-08-30 | 250000 |  | WARD ASSET MANAGEMENT INC. | Church | Consultant Fee
| 6 | 1 |  |  |  | 06012015 | 2020-06-01 | 750000 |  | WARD ASSET MANAGEMENT INC. | Church | Consultant Fee
| 8 | 3 |  |  |  | 915133 |  | 846 |  | WCD Group | Environmental Consultant
| 8 | 3 |  |  |  | 915134 |  | 622 |  | WCD Group | Environmental Consultant
| 19 | 1 |  |  |  | 27692 | 2015-05-12 | 5050 | Jon Hu | WCD Group- Emteque | Environmental Consultant | Environmental | Asbestos Survey
| 303 | 1 |  |  |  |  | 2015-07-01 | 9027.21 |  | CONNECT ONE BANK |  | 6/15 interest
Total | [7 empty] | 1000000
Developer Approval: |  |  | Date
√
√-
NA
No

## Reallocations (hidden)
| Budget Reallocations |  |  |  |  | All Budget Reallocations for Column 2 must be entered on this table
Date Issued | Dated Submitted for Owner Approval | Date Approved by Owner | Advance Request | Ref No. | CR Ref | Budget Line # Impacted | Reallocation for: | Description | Reallocation Incr/(Decr)
1.31.12 | 1.31.12 | 1.31.12 | 7 | R033 |  | 1510
1.31.12 | 1.31.12 | 1.31.12 | 7 | R032 |  | 1515
1.31.12 | 1.31.12 | 1.31.12 | 7 | R028 |  | 1520
1525
9.30.11 | 9.30.11 | 9.30.11 | 3 | R001 | DJ0001 | 1545
1.31.12 | 1.31.12 | 1.31.12 | 7 | R034 |  | 1545
9.30.11 | 9.30.11 | 9.30.11 | 3 | R002 |  | 1550
1.31.12 | 1.31.12 | 1.31.12 | 7 | R035 |  | 1550
10.31.11 | 10.31.11 | 10.31.11 | 4 | R003 |  | 1555
1.31.12 | 1.31.12 | 1.31.12 | 7 | R036 |  | 1555
10.31.11 | 10.31.11 | 10.31.11 | 4 | R004 |  | 1560
1.31.12 | 1.31.12 | 1.31.12 | 7 | R037 |  | 1560
1.31.12 | 1.31.12 | 1.31.12 | 7 | R038 |  | 1565
10.31.11 | 10.31.11 | 10.31.11 | 4 | R005 |  | 2001
1.31.12 | 1.31.12 | 1.31.12 | 7 | R039 |  | 2001
10.31.11 | 10.31.11 | 10.31.11 | 4 | R006 |  | 2002
10.31.11 | 10.31.11 | 10.31.11 | 4 | R007 |  | 2004
1.31.12 | 1.31.12 | 1.31.12 | 7 | R040 |  | 2004
10.31.11 | 10.31.11 | 10.31.11 | 4 | R008 |  | 2005
1.31.12 | 1.31.12 | 1.31.12 | 7 | R041 |  | 2005
10.31.11 | 10.31.11 | 10.31.11 | 4 | R009 |  | 2006
1.31.12 | 1.31.12 | 1.31.12 | 7 | R042 |  | 2006
10.31.11 | 10.31.11 | 10.31.11 | 4 | R010 |  | 2007
1.31.12 | 1.31.12 | 1.31.12 | 7 | R043 |  | 2007
10.31.11 | 10.31.11 | 10.31.11 | 4 | R011 |  | 2008
1.31.12 | 1.31.12 | 1.31.12 | 7 | R044 |  | 2008
10.31.11 | 10.31.11 | 10.31.11 | 4 | R012 |  | 2009
1.31.12 | 1.31.12 | 1.31.12 | 7 | R045 |  | 2009
10.31.11 | 10.31.11 | 10.31.11 | 4 | R013 |  | 2010
10.31.11 | 10.31.11 | 10.31.11 | 4 | R014 |  | 2015
10.31.11 | 10.31.11 | 10.31.11 | 4 | R015 |  | 2021
10.31.11 | 10.31.11 | 10.31.11 | 4 | R016 |  | 2025
10.31.11 | 10.31.11 | 10.31.11 | 4 | R017 |  | 2035
1.31.12 | 1.31.12 | 1.31.12 | 7 | R047 |  | 2050
1.31.12 | 1.31.12 | 1.31.12 | 7 | R048 |  | 2055
10.31.11 | 10.31.11 | 10.31.11 | 4 | R018 |  | 2056
1.31.12 | 1.31.12 | 1.31.12 | 7 | R049 |  | 2056
10.31.11 | 10.31.11 | 10.31.11 | 4 | R019 |  | 2057
1.31.12 | 1.31.12 | 1.31.12 | 7 | R050 |  | 2057
11.30.11 | 11.30.11 | 11.30.11 | 5 | R020 |  | 2058
1.31.12 | 1.31.12 | 1.31.12 | 7 | R054 |  | 2058
11.30.11 | 11.30.11 | 11.30.11 | 5 | R021 |  | 2060
1.31.12 | 1.31.12 | 1.31.12 | 7 | R046 |  | 2061
1.31.12 | 1.31.12 | 1.31.12 | 7 | R051 |  | 2062
11.30.11 | 11.30.11 | 11.30.11 | 5 | R022 |  | 2065
1.31.12 | 1.31.12 | 1.31.12 | 7 | R053 |  | 2065
1.31.12 | 1.31.12 | 1.31.12 | 7 | R052 |  | 2066
1.31.12 | 1.31.12 | 1.31.12 | 7 | R055 |  | 2505
4.30.12 | 4.30.12 | 4.30.12 | 10 | R065 |  | 2511
2.29.12 | 2.29.12 | 2.29.12 | 8 | R057 |  | 2515
2.29.12 | 2.29.12 | 2.29.12 | 8 | R056 |  | 2516
2.29.12 | 2.29.12 | 2.29.12 | 8 | R058 |  | 2517
3.31.12 | 3.31.12 | 3.31.12 | 9 | R063 |  | 2520
4.30.12 | 4.30.12 | 4.30.12 | 10 | R064 |  | 2525
2.29.12 | 2.29.12 | 2.29.12 | 8 | R059 |  | 2530
4.30.12 | 4.30.12 | 4.30.12 | 10 | R066 |  | 2531
2.29.12 | 2.29.12 | 2.29.12 | 8 | R060 |  | 2540
2.29.12 | 2.29.12 | 2.29.12 | 8 | R061 |  | 2565
11.30.11 | 11.30.11 | 11.30.11 | 5 | R023 |  | 2570
4.30.12 | 4.30.12 | 4.30.12 | 10 | R067 |  | 2570
4.30.12 | 4.30.12 | 4.30.12 | 10 | R068 |  | 2572
12.31.11 | 12.31.11 | 12.31.11 | 6 | R024 |  | 2575
3.31.12 | 3.31.12 | 3.31.12 | 9 | R062 |  | 2575
3005
3010
4.30.12 | 4.30.12 | 4.30.12 | 10 | R069 |  | 3505
4.30.12 | 4.30.12 | 4.30.12 | 10 | R070 |  | 3506
4.30.12 | 4.30.12 | 4.30.12 | 10 | R071 |  | 3510
12.31.11 | 12.31.11 | 12.31.11 | 6 | R025 |  | 6000
1.31.12 | 1.31.12 | 1.31.12 | 7 | R026 |  | 6500
4.30.12 | 4.30.12 | 4.30.12 | 10 | R072 |  | 6500
1.31.12 | 1.31.12 | 1.31.12 | 7 | R027 |  | 6505
4.30.12 | 4.30.12 | 4.30.12 | 10 | R073 |  | 6505
1.31.12 | 1.31.12 | 1.31.12 | 7 | R029 |  | 6515
1.31.12 | 1.31.12 | 1.31.12 | 7 | R030 |  | 7020
1.31.12 | 1.31.12 | 1.31.12 | 7 | R031 |  | 7025
5.31.12 | 5.31.12 | 5.31.12 | 11 | R074
5.31.12 | 5.31.12 | 5.31.12 | 11 | R075
5.31.12 | 5.31.12 | 5.31.12 | 11 | R076
5.31.12 | 5.31.12 | 5.31.12 | 11 | R077
5.31.12 | 5.31.12 | 5.31.12 | 11 | R078
5.31.12 | 5.31.12 | 5.31.12 | 11 | R079
5.31.12 | 5.31.12 | 5.31.12 | 11 | R080
6.30.12 | 6.30.12 | 6.30.12 | 12 | R081
6.30.12 | 6.30.12 | 6.30.12 | 12 | R082
6.30.12 | 6.30.12 | 6.30.12 | 12 | R082
6.30.12 | 6.30.12 | 6.30.12 | 12 | R083
6.30.12 | 6.30.12 | 6.30.12 | 12 | R084
6.30.12 | 6.30.12 | 6.30.12 | 12 | R085
6.30.12 | 6.30.12 | 6.30.12 | 12 | R086
6.30.12 | 6.30.12 | 6.30.12 | 12 | R087
7.31.12 | 7.31.12 | 7.31.12 | 13 | R088
7.31.12 | 7.31.12 | 7.31.12 | 13 | R089
8.31.12 | 8.31.12 | 8.31.12 | 14 | R090
8.31.12 | 8.31.12 | 8.31.12 | 14 | R091
8.31.12 | 8.31.12 | 8.31.12 | 14 | R092
8.31.12 | 8.31.12 | 8.31.12 | 14 | R093
8.31.12 | 8.31.12 | 8.31.12 | 14 | R094
8.31.12 | 8.31.12 | 8.31.12 | 14 | R095
8.31.12 | 8.31.12 | 8.31.12 | 14 | R096
8.31.12 | 8.31.12 | 8.31.12 | 14 | R097
9.30.12 | 9.30.12 | 9.30.12 | 15 | R098
9.30.12 | 9.30.12 | 9.30.12 | 15 | R099
9.30.12 | 9.30.12 | 9.30.12 | 15 | R100
9.30.12 | 9.30.12 | 9.30.12 | 15 | R101
9.30.12 | 9.30.12 | 9.30.12 | 15 | R102
9.30.12 | 9.30.12 | 9.30.12 | 15 | R103
9.30.12 | 9.30.12 | 9.30.12 | 15 | R104
10.31.12 | 10.31.12 | 10.31.12 | 16 | R105
10.31.12 | 10.31.12 | 10.31.12 | 16 | R106
10.31.12 | 10.31.12 | 10.31.12 | 16 | R107
10.31.12 | 10.31.12 | 10.31.12 | 16 | R108
11.30.12 | 11.30.12 | 11.30.12 | 17 | R109
11.30.12 | 11.30.12 | 11.30.12 | 17 | R110
11.30.12 | 11.30.12 | 11.30.12 | 17 | R111
11.30.12 | 11.30.12 | 11.30.12 | 17 | R112
11.30.12 | 11.30.12 | 11.30.12 | 17 | R113
11.30.12 | 11.30.12 | 11.30.12 | 17 | R114
11.30.12 | 11.30.12 | 11.30.12 | 17 | R115
11.30.12 | 11.30.12 | 11.30.12 | 17 | R116
1.31.13 | 1.31.13 | 1.31.13 | 19 | R117
1.31.13 | 1.31.13 | 1.31.13 | 19 | R118
1.31.13 | 1.31.13 | 1.31.13 | 19 | R119
1.31.13 | 1.31.13 | 1.31.13 | 19 | R120
1.31.13 | 1.31.13 | 1.31.13 | 19 | R121
1.31.13 | 1.31.13 | 1.31.13 | 19 | R122
1.31.13 | 1.31.13 | 1.31.13 | 19 | R123
1.31.13 | 1.31.13 | 1.31.13 | 19 | R124
1.31.13 | 1.31.13 | 1.31.13 | 19 | R125
1.31.13 | 1.31.13 | 1.31.13 | 19 | R126
2.28.13 | 2.28.13 | 2.28.13 | 20 | R127
2.28.13 | 2.28.13 | 2.28.13 | 20 | R128
2.28.13 | 2.28.13 | 2.28.13 | 20 | R129
2.28.13 | 2.28.13 | 2.28.13 | 20 | R130
3.31.13 | 3.31.13 | 3.31.13 | 21 | R131
3.31.13 | 3.31.13 | 3.31.13 | 21 | R132
3.31.13 | 3.31.13 | 3.31.13 | 21 | R133
3.31.13 | 3.31.13 | 3.31.13 | 21 | R134
3.31.13 | 3.31.13 | 3.31.13 | 21 | R135
3.31.13 | 3.31.13 | 3.31.13 | 21 | R136
4.30.13 | 4.30.13 | 4.30.13 | 22 | R137
4.30.13 | 4.30.13 | 4.30.13 | 22 | R138
4.30.13 | 4.30.13 | 4.30.13 | 22 | R139
4.30.13 | 4.30.13 | 4.30.13 | 22 | R140
4.30.13 | 4.30.13 | 4.30.13 | 22 | R141
4.30.13 | 4.30.13 | 4.30.13 | 22 | R142
5.31.13 | 5.31.13 | 5.31.13 | 23 | R143
5.31.13 | 5.31.13 | 5.31.13 | 23 | R144
5.31.13 | 5.31.13 | 5.31.13 | 23 | R145
5.31.13 | 5.31.13 | 5.31.13 | 23 | R146
5.31.13 | 5.31.13 | 5.31.13 | 23 | R147
5.31.13 | 5.31.13 | 5.31.13 | 23 | R148
5.31.13 | 5.31.13 | 5.31.13 | 23 | R149
5.31.13 | 5.31.13 | 5.31.13 | 23 | R150
5.31.13 | 5.31.13 | 5.31.13 | 23 | R151
6.30.13 | 6.30.13 | 6.30.13 | 24 | R152
6.30.13 | 6.30.13 | 6.30.13 | 24 | R153
6.30.13 | 6.30.13 | 6.30.13 | 24 | R154
7.31.13 | 7.31.13 | 7.31.13 | 25 | R155
7.31.13 | 7.31.13 | 7.31.13 | 25 | R156
7.31.13 | 7.31.13 | 7.31.13 | 25 | R157
7.31.13 | 7.31.13 | 7.31.13 | 25 | R158
7.31.13 | 7.31.13 | 7.31.13 | 25 | R159
7.31.13 | 7.31.13 | 7.31.13 | 25 | R160
9.30.13 | 9.30.13 | 9.30.13 | 26 | R161
9.30.13 | 9.30.13 | 9.30.13 | 26 | R162
9.30.13 | 9.30.13 | 9.30.13 | 26 | R163
9.30.13 | 9.30.13 | 9.30.13 | 26 | R164
9.30.13 | 9.30.13 | 9.30.13 | 26 | R165
9.30.13 | 9.30.13 | 9.30.13 | 26 | R166
9.30.13 | 9.30.13 | 9.30.13 | 26 | R167
9.30.13 | 9.30.13 | 9.30.13 | 26 | R168
9.30.13 | 9.30.13 | 9.30.13 | 26 | R169
9.30.13 | 9.30.13 | 9.30.13 | 26 | R170
9.30.13 | 9.30.13 | 9.30.13 | 26 | R171
9.30.13 | 9.30.13 | 9.30.13 | 26 | R172
9.30.13 | 9.30.13 | 9.30.13 | 26 | R173
9.30.13 | 9.30.13 | 9.30.13 | 26 | R174
9.30.13 | 9.30.13 | 9.30.13 | 26 | R175
9.30.13 | 9.30.13 | 9.30.13 | 26 | R176
0
Total | [8 empty] | 0

## Change Requests
| Change Request Log |  |  |  | Change Orders are applicable to all changes to Hard and Soft cost items, including FF&E
Use Pending items to identify potential changes which may impact the Renovation
Use reallocation to adjust the Project Budget when Estimated Final Cost for item exceeds thye line Item Budget.
Date Recorded | 15 day Submission Deadline | Approval by Lender Reqd? | Lender Approval Status | Date Lender pproved | RFI Reference | Change Request Ref No. | ID # Impacted | Invoice | Description | CR Approved Date (must enter to calc values) | CR Amount | Approved | Pending
|  | No | [8 empty] | 0 | 0 | 0
|  | Yes | [8 empty] | 0 | 0 | 0
|  | No | [8 empty] | 0 | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
|  | No | [9 empty] | 0 | 0
Do not use this row
Total | [10 empty] | 0 | 0 | 0
Approval Not Required
Approved by Borrower
Submitted, Under Review by Lender
Approved by Lender
Not Approved
Approved by Default
Voided